PROCEEDURE FOR SUBMITTING EAGLE LEADERSHIP PROJECTS

An Eagle Leadership Project is  requirement #5 for the rank of Eagle Scout where you are to demonstrate your abilities to PLAN, ORGANIZE and LEAD to a successful completion of a community service project.  NOT DO YOURSELF.  You will need to show and describe how you will show your leadership skills while performing this project.

- Briefly discuss your idea with the Scoutmaster or Eagle Coach.

- If given the go ahead to start planning, read and complete pages 1 to 10 of the Eagle Leadership Project Workbook and send an electronic copy to the Scoutmaster or Eagle Coach.  Once approval of proposal is received, Scout should then start to do the full plan and describe the project DETAILS.  Starting on Page 11.

- Your plan must be written in such a way that if you were to give it to another scout, he should be able to follow your details and complete the project without you.  Think of this as “Your Eagle Project for Dummies” book.

- If you are going to build something, you must have DETAILED plans with dimensions and a bill of materials with cost of all materials, equipment and supplies.  You must tell how the materials will be obtained.

- Make a time line for your project.  EXAMPLE:  Meet at 8:00 AM.  Safety lecture at 8:15 AM.  Phase 1 completed by 10:00 AM.  Lunch at 12:00 Noon.  Finished by 3:30 PM.  Clean up finished by 4:30 PM.  Final project report and changes entered into project workbook 2 weeks after work is completed.  Final approval signatures obtained 1 week after final write up.

- You must describe any Safety Hazards you may encounter and explain how you will ensure the safety of those carrying out the project.  The Troop committee MUST be told the date you plan on doing the project to place on the Troop calendar and to insure it does not conflict with another event already planned.

- If you are planning to campout along with your project, you must follow the BSA guidelines for planning a campout which includes your camping plan as described in the Camping Merit Badge book, ’Leave No Trace’ policy must be adhered to, Permission slips and a Tour Plan must be secured.

- If you are going to travel more than 50 miles in one direction and less than 500 miles to your project site, you must secure a Tour Plan and permission slips for Scouts attending.

- If you are going to do a Fund Raiser to raise the money to purchase or request donations of the materials for your project, you must submit a Fund Raising request form to the Council office AND possibly your Charter Organization.  See pages 21 & 22 in the workbook for detailed info on fund raisers.

- If you are planning on constructing a structure such as a storage shed on the site of your school, church, a city park or where ever, you WILL need a Building Permit.  A licensed contractor will be needed to obtain the permit on your behalf.  If you can find one.

- What is your contingency plan?

- An electronic copy should be submitted to the Scoutmaster or Eagle Coach to be distributed to other leaders within the troop for review and comments.  No one individual should approve a project without input from other adult leaders in the Troop.

- Before the Troop can approve your project, you must obtain the signed approval from the representative you are doing the project for.  Then the Scoutmaster or his designee and a Troop committee member.  Then you must contact the Frontier District Advancement Chairperson to obtain District/Council approval.  You cannot start your project before obtaining all approvals.

GOOD LUCK